## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | STUDENT INFORMATION SYSTEM |  |  |  |  | COMPANY NAME | [6 empty] | DU SIS
PROJECT MANAGER |  | MR. FRANK ANTHONY R. CHIN |  |  |  |  | DATE | [6 empty] | 2023-01-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Desiree Uranza | 2018-03-12 | 2022-12-19 | 1717 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions | Desiree Uranza | 2023-01-16 | 2023-01-16 | 0 | 100% | bar: WEEK 2 W
1.2 | Udate Flowchart | Desiree Uranza | 2023-01-16 | 2023-01-16 | 0 | 90% | bar: WEEK 2 W to WEEK 3 W
1.3 | Database Structure | Desiree Uranza | 2023-01-16 | 2023-01-16 | 0 | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 | Create Git Repository | Desiree Uranza | 2023-01-16 | 2023-01-16 | 0 | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 | Initial Code | Desiree Uranza |  |  | 0 | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 | Project Initiation | Desiree Uranza |  |  | 0 | 50% | bar: WEEK 3 F
2 | Menu Function
2.1 | 1. sign up new students | Desiree Uranza | 2018-03-24 |  | 4 | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 | 2. view records | Desiree Uranza | 2018-03-29 |  | 3 | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 | 3. Edit Records | Desiree Uranza |  |  | 0 | 0%
2.4 | 4. Delete Records | Desiree Uranza |  |  | 0 | 0%
3 | Project Conception and Initiation
3.1 | Coding |  |  |  | 0 | 0%
3.2 | Testing |  |  |  | 0 | 0%
3.2.1 | Monitoring |  |  |  | 0 | 0%
3.2.2 | Forecasts |  |  |  | 0 | 0%
3.3 | Project Updates |  |  |  | 0 | 0%
3.3.1 | Chart Updates |  |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  |  |  | 0 | 0%
4.2 |  |  |  |  | 0 | 0%
4.3 |  |  |  |  | 0 | 0%
4.4 | Project Performance |  |  |  | 0 | 0%